## Sheet1
Task | Assignee | Estimate
Add Viewable Shopping List Page to Web | Alexander Ayers | 2
Add Logout and Redirect of Index on Login to Web | Alexander Ayers | 1
Add View Recipe Button for Planned Meals on Web | Alexander Ayers | 1
Have No on Planned Meals Confirmation Swap to Recipe Page on Web | Alexander Ayers | 1
Add Shopping List Ingredients From Web | Alexander Ayers | 2
Remove All Ingredients Used For Recipe on Web | Alexander Ayers | 2
Add Recipe Tags on Recipe List on Web | Alexander Ayers | 2
Add All Ingredients on Server | Alex Decesare | 3
Remove All Ingredients Used For Recipe on Server | Alex Decesare | 3
Add Shopping List to Desktop | Shawn Carter | 3
Add Shopping List Ingredients From Desktop | Shawn Carter | 2
Remove All Ingredients Used For Recipe on Desktop | Shawn Carter | 2
Add Collapsible Planned Meals on Desktop | Shawn Carter | 2
Add View Recipe Button for Planned Meals on Desktop | Shawn Carter | 1
Make Recipe Filters Static on Desktop | Shawn Carter | 1
Make Recipe Filters Static on Web | Alexander Ayers | 1
Fix Pop-Ups on Web For Planned Meals not Unhiding Other | Alexander Ayers | 1